## Change_Log (hidden)
Change Log:
Change number | Date of change | Description | Change originator | Change documentation
Version 02
LT01 | 2014-01-20 | Announced new tenders from Facility management | S. Adam
Version 03
LT02 | 2014-01-22 | 1) added Procurement representatives to unassigned tenders; 2) added initial tender codes for future refference; 3) added new column "Group number" -it will serve for merging proposals for similar nature tenders | A. Oláh | n/A
Version 04
LT03 | 2014-02-07 | 1) changed name of tender TP14_011 from "Routers Dolní Břežany" | J. Charfreitag
|  | 2) modified start dates for SE tenders; tender TP14_043, 054, 080 removed | B. Le Garrec
|  | 3) applied first merging proposalas: resulted in 107 tenders in total; merged tenders have identical Group number | A. Oláh
|  | 4) added new tenders | A. Oláh
Version 05
LT04 | 2014-02-28 | Updated status info for running tenders, shifted start dates for delayed ones; TP14_003, 005, 054, 084 finished. TP14_95, 96, 100, 105 removed, TP14_110 moved into year 2015 and got new ref. no. TP15_110 new tenders TP14_128, 129 | A. Oláh
Version 06
LT05 | 2014-03-28 | 1) added new items TP14_130, 131 | V. Krpálková
|  | 2) TP14_108 canceled in 2014 (former name "Optomechanics for exp. programmes"); changed its RP's validity (now only RP4, RP5) and moved into 2015 TP14_078 renamed (former name "Small (<4 inches) Optics"); changed its RP's validity (now only RP2, RP3); merged with TP14_036; TP14_129 renamed (former name "Instrumentation & Controls") merged with TP14_041; | V. Krpálková
|  | 3) new item TP14_132, merged with L1 "Optical tables TP14_060" | V. Krpálková
|  | 4) new item TP14_133, merged with SE "CS HW: Timing & delay generators" | V. Krpálková
|  | 5) TP14_120 out of merging with 082 & 094 due to different timing | A. Oláh
|  | 6) P. Bakule postponed TP14_053, 091 | D. Kurz
|  | 7) TP14_061 merged-out of group (T14_060+123) | M. Legát
|  | 8) scheduling confronted according to Master Plan 01/2014 and SoWs for Exp, SE | D. Myslikovjan
|  | 9) in general added more columns describing planning process and deadline assesment | D. Myslikovjan
Version 07
LT06 | cw14/2014 | 1) tenders TP14_076+122 were merged out; TP14_122 continues as Small Cost | D. Kurz
| cw17/2014 | 2) TP14_125 start postponed due to delayed tech. spec | D. Kurz
| cw17/2014 | 3) TP14_081 and TP14_093 merged | D. Kurz
| cw17/2014 | 4) TP14_051 canceled in 2014 (lack of money); for now postponed to 2015 | D. Kurz
| cw18/2014 | 5) TP14_031 and TP14_033 merged; timing data aligned according to TP14_031; postponed from 05/2014 to 09/2014 | B. Le Garrec
| cw18/2014 | 6) TP14_126 CANCELED; re-launched as TP14_136 | A. Csabová
| cw18/2014 | 7) TP14_006 postponed start date due to tender nature (continuosly running minitenders) | A. Csabová
| cw18/2014 | 8) TP14_010 postponed start for 2 months (missing tech. spec.) | D. Pokorný
| cw18/2014 | 9) added SW licences tenders TP14_134+135 (Matlab, Office Packages -period 2014/2015) | A. Csabová
| cw18/2014 | 10) Calorimeters tender broken down to TP14_027 (L1 - E1 branch) and TP14_137 (other branches); both postponed from 17.4.2014 | B. Le Garrec
| cw18/2014 | 11) TP14_029 and TP14_035 have been out-merged; TP14_029 postponed from 04/2014; TP14_035 moved to 2015 from 04/2014 | B. Le Garrec
| cw18/2014 | 12) TP14_32 and TP14_079 (TMP pumps) -start postponed to mid from 06/2014 to 09/2014 | M. Legát
| cw18/2014 | 13) TP14_060 (L1 Optical tables) postponed from 04/2014 to 05/2014 | M. Legát
| cw18/2014 | 14) TP14_045+046 postponed for 1 month from 05/2014 | B. Le Garrec
| cw18/2014 | 15) TP14_034+036(+Exp 078) postponed for 2M from 01/04/2014; break-down to 2+ tenders in consideration | B. Le Garrec
| cw18/2014 | 16) TP14_042 (+Exp 133) postponed for 1M from 01/05/2014 | B. Le Garrec
| cw18/2014 | 17) TP14_089 tender canceled, decided to order as a part of L3 LLNL contract | M. Legát
| cw18/2014 | 18) TP14_090 postponed from 17/04/2014 due to missing tech spec | B. Rus
| cw18/2014 | 19) TP14_104 delay 1M due to delay on tech spec approval | D. Pokorný
| cw18/2014 | 20) TP14_113 new rough schedule added; start expected by 09/2014 | D. Pokorný
| cw18/2014 | 21) TP14_118+119 postponed from 04/2014 to 09/2014 | P. Korouš
| cw18/2014 | 22) added TP14_138+139 -tenders originating in 2013 but pose proc/admin load in 2014 | A. Csabová
| cw18/2014 | 23) added TP14_140 -tender originates in 2013 but poses proc/admin load in 2014 | A. Csabová
| cw19/2014 | 24) added TP14_141 -re-launched 2nd part of L1 B1B2 compressor optics | D. Pokorný
Version 08
LT07 | cw20/2014 | 1) added TP14_142 (3rd Scientific Challenges Workshop) | M. Vích
| cw20/2014 | 2) postponed TP14_10 and TP14_120 to end of 06/2014 due to missing specification/design | D. Pokorný
| cw22/2014 | 3) added TP14_143: Vacuum equipment L1-E1 including vacuum vessels | R. Ther
| cw22/2014 | 4) former TP14_060 has been broken down to 2 new tenders: TP14_060 (L1 + Exp tables) and TP14_144 (L2/L3 tables) | M. Legát
| cw22/2014 | 5) TP14_015 canceled, only local privileged supplier is available | D. Pokorný
| cw22/2014 | 6) updated price estimations for TP14_019, 021 and TP14_125 | S. Adam
| cw22/2014 | 7) TP14_125 postponed from 2.6.2014 due to missing specification to 30.7.2014; this causes delay 2,2 months to actual deadline | S. Adam
| cw23/2014 | 8) TP14_067+068+069 postponed start from 06/2014 -according to updated L1 planning in MP 05/2014 | D. Myslikovjan
| cw23/2014 | 9) TP14_097 postponed to 07/2014: scientists rely on excemption buy thus shorter administration time | D. Kurz
| cw23/2014 | 10) added TP14_145: tender for Stage S1 optics of L1 main OPCPA | D. Myslikovjan
| cw23/2014 | 11) added TP14_146 - VZMR | A. Csabová
| cw23/2014 | 12) due to delayed/tentative design postponed (2-4M) folowing L1 procurements: TP14_055, 058, 059, 123, 062, 064, 065, 066 TP14_057, 074 postponed also and possibly will be subject to Small Cost breakdown | P. Bakule
| cw23/2014 | 13) updated price estimations for TP14_027 and TP14_137 (this was also renamed) | A. Csabová
| cw23/2014 | 14) canceled tender TP14_092 - it is already realised via Small Cost/Excemptional purchases | P. Bakule
| cw23/2014 | 15) changed deadline and delivery duration for TP14_076 -based on approved contract draft is deadline postponed from 1/8/2014 to 15/12/2014; delivery duration changed from 5M to 2M (contract draft) | P. Bakule
| cw23/2014 | 16) TP14_081+093 (L2 OPCPA Stage 1) prolonged negotiation phase from 4M to 9M | D. Kurz
| cw23/2014 | 17) TP14_092 - L2 Stage1 dependent contract, posptponed start from 26/06/2014 to 09/2014 | D. Myslikovjan
| cw23/2014 | 18) TP14_083 + 085 + 087 changed duration of contracting phase from 40D to 10D (to be realised via MEYS Excemtion); also postponed about 2M -there is no procurement request yet | M. Legát
| cw23/2014 | 19) TP14_089: changed classification from CANCELED to CONTRACTED | D. Myslikovjan
| cw23/2014 | 20) added new column named "Progress phase"; column states status of administration for already started tender | D. Myslikovjan
| cw23/2014 | 21) TP14_101 canceled | B. Rus
Version 09
LT08 | cw25/2014 | 01) added TP14_147 - L1_LBO_OPCPA_crystals_main_amp;new entry from PBS database | D. Myslikovjan
| cw26/2014 | 02) TP14_020 canceled; ELI will use iFIS IS in early ELI operation phase | M. Chudožilov
| cw27/2014 | 03) TP14_102 (kJ laser 4) contracting process failed; old tender marked as CANCELED; new contracting phase listed as new tender under ref. number TP14_148 | M. Legát
| cw27/2014 | 04) TP14_134 procurement informed about start of demanded tender | A. Csabová
| cw27/2014 | 05) Added new TP14_149 - Office SW licences for period 2015-2016 | A. Csabová
| cw27/2014 | 06) TP14_136 (Twinning partners) start again re-issued from 07/05/2014 to 01/07/2014 | A. Csabová
| cw28/2014 | 07) TP14_140 tracked 3rd launch: changed start (from 26.2.2014 to 23.4.2014), Latest publication date and status | A. Csabová
| cw28/2014 | 08) added TP14_150; it substitues failed TP14_138; deliverables from this tender are than logically delayed - now 1/2 year | A. Csabová
| cw28/2014 | 09) TP14_141: 4th repetition loop thus deadline was postponed accordingly by Laser 1 team leader from 20/11/2014 to 01/01/2015 | P. Bakule
| cw28/2014 | 10) TP14_010 for 1M postponed start from 30/06/2014 due to missing specifications | D. Pokorný
| cw28/2014 | 11) TP14_103 (HHG) referrence deadline changed from 29/10/2015 to 08/09/2015 (from Master Schedule); this in addition with delayed publication of tender causing total delay of 7 months | D. Pokorný D. Myslikovjan
| cw28/2014 | 12) TP14_104 (kAlpha): referrence deadline changed from 30/11/2015 to 08/09/2015 (from Master Schedule); tech specification is not yet finished; start of tender postponed from 05/2014 to 07/2014; absolute delay changed from 6M to 11M | D. Pokorný
| cw28/2014 | 13) TP14_106 (Elimed): referrence deadline changed from 11/07/2017 to 28/02/2017 (from Master Schedule); leadtime duration prolonged from 28M to 32M (based on info from Master Schedule); updated price (previously 67M CZK ex VAT) | D. Pokorný
| cw28/2014 | 14) TP14_034(and merged 036 + Exp 078, 111): SE part tech. specifications delayed; start postponed from 05/2014 to 30/07/2014 | A. Csabová
| cw28/2014 | 15) TP14_042 (and merged Exp 133): postponed start from 01/06/2014 to 01/08/2014 due to missing (and dependent) specifications inside SE team | A. Csabová
| cw28/2014 | 16) TP14_130: postponed start (1,5M) from 01/06/2014 due to missing specification | D. Pokorný
| cw28/2014 | 16) TP14_112: postponed start (2,0M) from 01/06/2014 due to missing specification; according to last version of RP4 SoW were: shortened delivery duration (from 18M to 12M) and changed deadline (from year 2016 to 01/11/2015) | D. Pokorný D. Myslikovjan
| cw28/2014 | 17) TP14_022: missing specification; start postponed for 2M from 02/06/2014 | A. Csabová
| cw28/2014 | 18) TP14_045 + 046: stopped by Management due to financing issues | A. Csabová
| cw28/2014 | 19) TP14_048: start postponed for 2M from 02/06/2014 due to missing specification | A. Csabová
| cw28/2014 | 20) TP14_071 (Osc. room for L1): civil engineering project delayed thus postponed also start of Proc activities from 05/2014 to 26/08/2014 | M. Chudožilov
| cw28/2014 | 21) TP14_137: specification unknown, start postponed from 06/2014 to 16/08/2014; changed justification deadline from 12/2015 to 06/2015 (= from SE SoW is used an end of Calorimetres contract) | D. Myslikovjan
| cw28/2014 | 22) TP14_037: specification unknown, start postponed from 06/2014 to 01/08/2014 | A. Csabová
| cw28/2014 | 23) TP14_038: specification unknown, start postponed from 05/2014 to 01/08/2014 | A. Csabová
| cw28/2014 | 24) TP14_044: specification unknown, start postponed from 06/2014 to 01/08/2014 | A. Csabová
| cw28/2014 | 25) added new column: Publication delay: it expresses delay of presently scheduled date of Publication compared to original schedule | A. Csabová
Version 10
LT09 | cw29/2014 | 01) added TP14_151 (Safety systems - design/project of gas & radiation monitoring system) | P. Procházka
| cw29/2014 | 02) based on documentation from RP4 leader was updated price for TP14_130 (RP4 VUV elipsometry station) | J. Andreasson
| cw30/2014 | 03) TP14_022 postponed from 08/2014 to 09/2014 due to missing technical specification | B. Le Garrec
| cw30/2014 | 04) TP14_028 postponed start from 01/07/2014 to 01/08/2014 due to vacation of SE responsible and missing specs | B. Le Garrec
| cw30/2014 | 05) TP14_030 postponed start from 07/2014 to 10/2014 by SE leader (equipment not necessary until L2, L3, L4 related BT will be installed) | R. Ther
| cw30/2014 | 06) aded TP14_152: new item derrived from TP14_034 (Opt. mounts for Beam Transport) | R. Ther
| cw31/2014 | 07) TP14_035: reverted back from 2015 to 11/2014 | B. Le Garrec
| cw31/2014 | 08) added TP14_154: new item derrived from TP14_036 (Opt. components for Beam Transport: mirrors) | R. Ther
| cw31/2014 | 09) TP14_037: start moved to 09/2014 from 08/2014 due to lack of tech. specification | B. Le Garrec
| cw31/2014 | 10) TP14_038: start moved to 10/2014 from 08/2014 due to lack of tech. specification | B. Le Garrec
| cw31/2014 | 11) TP14_041 + 129 (merged): SE leader postponed driving tender 041 from 08/2014 to 11/2014 due to unprepared specification | P. Bastl
| cw31/2014 | 12) TP14_039 (CS HW: computers): start postponed from 07/2014 to 08/2014 due to specifications dependency on Beam Transport concept. In consideration is brake-down to four tenders or tender parts: Servers / Control PC / Diagnostic PC / Network components | P. Bastl
| cw31/2014 | 13) TP14_042 + 133 (merged): SE responsible postponed driving tender 042 from 08/2014 to 09/2014 due to unprepared specification | P. Bastl
| cw31/2014 | 14) TP14_048: start postponed from 08/2014 to 11/2014; SE leader states no need of this equipment before year 2017 | B. Le Garrec
| cw31/2014 | 15) TP14_049: start postponed from 10/2014 to 11/2014; SE leader states no need of this equipment before year 2017 | B. Le Garrec
| cw31/2014 | 16) TP14_050: start postponed from 11/2014 to 02/2015; SE leader states no need of this equipment before year 2017 | B. Le Garrec
| cw31/2014 | 17) added TP14_153: new item on request from RP5 leader | S. Weber
| cw31/2014 | 18) added TP14_156: formerly scheduled to 2015; on request from RP5 leader moved to 2014 | D. Pokorný
| cw31/2014 | 19) TP14_120: rescheduled start from 06/2014 to 10/2014 according to new informations from Proc; changed price from 9M to 35M; changed deadline according to soonest scheduled realization (RP3) in Master Schedule; changed leadtime | D. Pokorný D. Myslikovjan
| cw31/2014 | 20) TP14_018, 019: missing specs, start postponed from 30/06/2014 to 15/09/2014 | D. Kurz
| cw31/2014 | 21) TP14_021: missing specs, start postponed from 30/06/2014 to 15/12/2014 | D. Kurz
| cw31/2014 | 22) TP14_053+091: missing specs, start postponed from 01/08/2014 to 01/12/2014; L1 team tends to avoid usage of such equipment | D. Kurz
| cw31/2014 | 23) TP14_058: missing specs, start postponed from 01/08/2014 to 10/2014 | D. Kurz
| cw31/2014 | 24) TP14_059: missing specs, start postponed from 01/10/2014 to 12/2014 | D. Kurz
| cw31/2014 | 25) TP14_063: missing specs, start postponed from 21/08/2014 to 12/2014; according to L1 leader item is not urgent | D. Kurz
| cw31/2014 | 26) TP14_069 + 145: L1 team plan to merge these tenders; schedule will use data from driving tender TP14_069 | D. Kurz
| cw31/2014 | 27) TP14_073: missing specs, start postponed from 09/2014 to 10/2014 | D. Kurz
| cw31/2014 | 28) TP14_074: missing specs, start postponed from 08/2014 to 10/2014 | D. Kurz
| cw31/2014 | 29) TP14_075: canceled, broken down to Small Cost purchases | D. Kurz
| cw31/2014 | 30) TP14_077: L1 leader shifted schedule for 1M 4M | D. Kurz
| cw31/2014 | 31) TP14_081+093: L2 Stage2 OPCPA Publication phase prolonged for 2M | D. Kurz
| cw31/2014 | 32) TP14_097: postponed start from 07/2014 to 10/2014 due to unfinished specification | D. Kurz
Version 11
LT10 | cw34/2014 | 01) added TP14_155: Marketing and promotional services | O. Lažanský
| cw34/2014 | 02) added TP14_157: RP5 Roughing pumps | D. Pokorný
| cw34/2014 | 03) added TP14_158: Study of user potential of HiLase research center | M. Körber
| cw36/2014 | 04) TP14_107 CANCELED and substituted by TP14_159 (same tender, new name, continued delay); changed price from 11M to 12,5 M; changed MP deadline according to new MP 08/2014 from 11/2015 to 1/2016; changed delivery duration from 12M to 6M | J. Andreasson D. Myslikovjan
| cw36/2014 | 05) TP14_130: changed price from 9,6 M to 8,9 M; Publication phase prolonged for 2 weeks (tender docs aren't approved) | D. Pokorný
| cw36/2014 | 06) added (re-issued) TP14_163: ELI 3rd scientific workshop | R. Kočová
| cw36/2014 | 07) added TP14_164: Legal services | M. Legát
| cw36/2014 | 08) TP14_010: start delayed for next 2M - missing specification | D. Pokorný
| cw36/2014 | 09) TP14_016, 017: delayed start form 30.6. to 15.9.2014; according to responsible person for specification tender scheduled too soon; spec missing | D. Pokorný
| cw36/2014 | 10) TP14_103: HHG - "publication" milestone delayed 3M due to applicants holidays; changed MP deadline from 09/15 to 12/15 according to new Master Schedule (version 08/2015) | D. Pokorný; D. Myslikovjan
| cw36/2014 | 10) TP14_104: kAlpha - Publication deadline prolonged for 1M from 08/2014 to 30.9.2014; changed MP deadline from 09/15 to 12/15 according to new Master Schedule (version 08/2015) | D. Pokorný; D. Myslikovjan
| cw36/2014 | 11) TP14_106: ELIMAIA - ELIMED - Contracting phase prolonged for 1M from 09/2014 to 30.10.2014; changed MP deadline from 02/17 to 04/17 according to new Master Schedule (version 08/2015) | D. Pokorný; D. Myslikovjan
| cw36/2014 | 12) TP14_153: changed price from 0,6 M to 8,1 M | D. Pokorný
| cw36/2014 | 13) TP15_002, 007, 012, 013 moved to 2014 from 2015 on request from RP5 leader; | D. Pokorný
| cw36/2014 | 14) TP14_165 (frame contract to L1 PXIe and CRIo equipment): new item | M. Legát
| cw36/2014 | 15) TP15_008, 014: new tenders announced by RP4 leader by end of 07/2014 | J. Andreasson
| cw36/2014 | 16) TP14_166 (Off Axis Parabola f1.5/45deg for L3): new item on request from D. Kramer | D. Kramer
| cw36/2014 | 17) TP14_128 failed due to no bid and start is RE-ISSUED to 15.10 2014 | D. Kurz
| cw36/2014 | 18) TP14_018 postponed start for 1M from 15/09/2014: missing specification | D. Kurz
| cw36/2014 | 19) TP14_019, 021 CANCELED for 2014; for ELI facility start will be sufficient procurements below 200k CZK; moved to 2015 | D. Kurz
| cw36/2014 | 20) TP14_125: postponed for 3M from 30/07/2014: missing specification | D. Kurz
| cw36/2014 | 21) TP14_136 (Twinning): several times re-launched, now again in 01/09/2014 | A. Csabová
| cw36/2014 | 22) TP14_124 failed an is subject to RE-ISSUE from 15/09/2014 | A. Csabová
| cw37/2014 | 23) TP14_116 scheduled as dependent on TP14_151 (start postponed from 01/08/2014 to 06/11/2014) | A. Csabová D. Myslikovjan
| cw37/2014 | 24) TP14_151: shortened administration time, changed Publication deadline from 29/09/2014 to 16/09/2014 | A. Csabová
| cw37/2014 | 25) TP14_115: changed responsible for specification - J. Janďourek replaced by L. Nims | A. Csabová
| cw37/2014 | 26) TP14_121: Nothing happens, needs to be managed immediately. First installations scheduled to mid of 2015 (L1-E1). Postponed start for 2M from 01/08/2014. to 1/10/2014 | D. Myslikovjan
| cw37/2014 | 27) TP14_120: changed MP deadline from 23.10.2015 to 30/01/2016 (soonest vac. chamber installation, RP2 Betatron, Master Schedule 08/2014) | D. Myslikovjan
| cw37/2014 | 28) TP14_028: changed MP deadline from 10/2014 to 08/2015 according Master Schedule 08/2014, changed delivery duration (3M->7M); postponed start due to missing specs and announced Negotiated procedure | A. Csabová
| cw37/2014 | 29) TP14_039: postponed start for 1M from 15/08/2014 - not finalized specifications | A. Csabová
| cw37/2014 | 30) TP14_027: based on MP 08/2014 were changed: delivery duration from 3M to 8M and delivery deadline from 12/2014 to 10/2015 | D. Myslikovjan
| cw37/2014 | 31) TP14_029: based on MP 08/2014 were changed: delivery duration from 3M to 7M and delivery deadline from 12/2014 to 08/2015 | D. Myslikovjan
| cw37/2014 | 32) TP14_071: Nobody reacted to Procurement request for tech. specification; postponed start from 26/08/2014 to 1/10/2014 | A. Csabová D. Myslikovjan
| cw37/2014 | 33) TP14_081: Administration stopped for 2M due to scope & budget revisions | D. Kurz
| cw37/2014 | 34) added TP14_167, 168, 169, 170: request from Procurement and responsible technician | A. Csabová
| cw37/2014 | 35) TP14_131 (former Raman probe): broken-down to 3 new tenders; this is the first one, new name, starting as soonest in 11/2014; MP deadline changed according to Master Schedule 08/2014 (from 09/2016 to 01/2016); price change from 20M to 11M CZK | J. Andreasson D. Myslikovjan
| cw37/2014 | 36) TP14_160 (former Raman probe): broken-down to 3 new tenders; this is the 2nd one, starting at 12/2014 | J. Andreasson
| cw37/2014 | 37) TP15_003 (former Raman probe): broken-down to 3 new tenders; this is the 3rd one, starting at 1/2015 | J. Andreasson
| cw37/2014 | 38) TP14_112: postponed start (from 8/2014 to 01/2015) due to missing specification, changing concept; according to last version of Master Schedule were: changed deadline (from year 11/2015 to 03/2016) | J. Andreasson D. Myslikovjan
| cw37/2014 | 39) added TP15_015, 016, 017, 018, 019, 020: new items based on info from RP4 leader | J. Andreasson
| cw37/2014 | 40) TP14_108 renumbered to TP15_108 as it is scheduled for year 2015 | D. Myslikovjan
| cw37/2014 | 41) TP14_050, 051, 052, 070, 110 renumbered to TP15_050, 051, 052, 070, 110 as they are scheduled for 2015 | D. Myslikovjan
| cw37/2014 | 42) added overview of tenders scheduled in 2015: filter Start column to string "in 2015" | D. Myslikovjan
Version 01 2015 (January)
LT11 | cw38/2014 | 01) TP14_170: CANCELED, equipment will be tendered within scope of TP14_169 | R. Ther
| cw38/2014 | 02) TP14_168: CANCELED, equipment will be tendered within scope of TP14_167 | R. Ther
| cw38/2014 | 03) TP14_099 (L3 PW compressor diagnostic beam optical components): based on statement from Laser team leader is further tracking of this tender stopped; will be realized via Small Cost procurements | B. Rus
| cw41/2014 | 04) added TP14_171: He Leak detector | L. Brabec
| cw48/2014 | 05) TP14_018 (Catering) moved to 02/2015 from 10/2014 | D. Kurz
| cw48/2014 | 06) TP14_163 (3rd scientific workshop) postponed from 10/2014 to 04/2015 | R. Kočová
| cw48/2014 | 07) TP14_019, 021 (Garbage mngmt & Laundry) set start to 04/2015 according to new Building schedule | D. Myslikovjan
| cw48/2014 | 08) TP14_125 (Furniture to conf. rooms) set start to 12/2014 according to new Building schedule and not-ready specifications | D. Myslikovjan
| cw50/2014 | 09) TP14_012, 013: postponed start from 30/7/2014 to 6/3/2015 according to new Building schedule and not-ready specifications | D. Myslikovjan
| cw50/2014 | 10) TP14_014: postponed start from 15/7/2014 to 16/2/2015 according to new Building schedule and not-ready specifications | D. Myslikovjan
| cw50/2014 | 11) TP14_016, 017: postponed start from 15/9/2014 to 16/2/2015 according to new Building schedule and not-ready specifications | D. Myslikovjan
| cw50/2014 | 12) TP14_062: Published by 24/11/2014 | M. Legát
| cw50/2014 | 13) TP14_069: out-merged from TP14_145, delayed Publication (1,5M) is OK with Master Plan 11/2014 | D. Myslikovjan
| cw51/2014 | 14) TP14_111: Removed from Group G034 and CANCELED, align. lasers realised via BDS team | D. Margarone
| cw02/2015 | 15) TP14_022: start postponed from 09/2014 due to delayed specs; new schedule according to Budget Phasing document ver. 13 | B. Le Garrec
| cw02/2015 | 16) TP15_002: tender Publication postponed due to newly added participant RP4 which has´t finished specifications yet | D. Pokorný
| cw02/2015 | 17) TP15_108: set initial tender Publication date to 20.03.2015 | D. Myslikovjan
| cw03/2015 | 18) TP14_023, 024, 025: tender scope changed to distribution branch L1-E1; starts postponed from fall/2014 | B. Le Garrec
| cw04/2015 | 19) TP16_001, 002, 003: new item scheduled to 2016 | B. Le Garrec
| cw04/2015 | 20) TP14_048: Neg. procedure approved by MEYS; Publication equivalent by end of 01/2015 | A. Csabová
| cw04/2015 | 21) TP14_094: postponed start of legal work of delayed tender to 9/2/2015; prelim. notice done in this week | D. Myslikovjan
| cw04/2015 | 22) TP14_052: tender approved as negotiation procedure; Publication Milestone equivalent scheduled to 04/2015 | D. Myslikovjan
| cw04/2015 | 22) TP14_053, 091: DAZZLERS tenders tracking stopped (marked tentative); administration on demand | D. Myslikovjan
| cw04/2015 | 23) TP14_058, 059, 077 canceled tenders, realization via Small Cost | D . Kurz
| cw04/2015 | 24) TP14_051: "Delay lines" tender tracking stopped (marked as tentative); administration on demand | D. Myslikovjan
| cw04/2015 | 25) TP15_070 moved to 2017 and thus renumbered to TP17_001 | D. Myslikovjan
| cw04/2015 | 26) TP15_022 moved to 2017 and thus renumbered to TP17_002 | D. Myslikovjan
| cw04/2015 | 27) TP14_173: new item; Published already by 12/2014 | M. Legát
| cw04/2015 | 28) TP14_072: new schedule according MP 11/2014 | D. Myslikovjan
| cw04/2015 | 29) TP14_067: new schedule according MP 11/2014 and new L1 sub-schedule | D. Myslikovjan
| cw04/2015 | 30) TP14_068: new schedule according MP 11/2014 and new L1 sub-schedule | D. Myslikovjan
| cw04/2015 | 31) TP15_038: new item | D. Myslikovjan
| cw04/2015 | 32) TP14_123: changed scope and schedule: from Alu parts to polycarbonate glass (Alu parts baught via TP14_173) | D. Myslikovjan
| cw04/2015 | 33) TP14_073: updated according to MP 11/2014; specification to be ready by end of 01/2015 | D. Myslikovjan
| cw04/2015 | 34) TP14_061: updated according to MP 11/2014 | D. Myslikovjan
| cw04/2015 | 35) TP14_063: tender canceled, ELI consider own design and production which still is being postponed | D. Myslikovjan
| cw04/2015 | 36) TP14_064, 065, 066: tenders tracking stopped (marked as tentative); administration on demand | D. Myslikovjan
| cw04/2015 | 37) TP14_032, 079: tenders tracking stopped (probably will be CANCELED and realized via dedicated tenders for other vacuum equipment) | D. Myslikovjan
| cw04/2015 | 38) TP15_021: tender found in PBS database, NOT present in MP 11/2014, but schedule confirmed by L1 leader | D. Myslikovjan
| cw04/2015 | 39) TP15_046, 022, 039: new items | J. Charfreitag
| cw04/2015 | 40) TP14_008, TP15_022, 025, 028: changed tender ACTUALS by J. Charfreitag | J. Charfreitag
| cw04/2015 | 41) TP15_040, 041, 042: new items | B. Le Garrec
| cw04/2015 | 42) TP14_118: postponed according to information of Engineering leader; scope changed from machine tools to mech. & electrical equipment | P. Korouš
| cw04/2015 | 43) TP14_143: start postponed from 09/2014 to 3/2/15 due to missing approved technical specification | B. Le Garrec
| cw04/2015 | 44) TP14_037: specifications are not ready; start postponed from 09/2014 to 30/01/2014 | B. Le Garrec
| cw04/2015 | 45) TP15_024: tender schedule updated based Master Plan deadlines of L1 system | D. Myslikovjan
| cw04/2015 | 46) TP14_028: postponed start of administration from 09/2014 to 01/2015 du to late specification | D. Kurz
| cw04/2015 | 47) TP14_031: tender canceled; substituted by new tenders TP15_040, 041, 042 | D. Myslikovjan
| cw04/2015 | 48) TP15_029-036: new items | P. Bastl
| cw04/2015 | 49) TP14_039, 040, 042: ACTUALS schedule changed according to information from CS HW team leader | P. Bastl
| cw04/2015 | 50) TP14_116, 117: starts postponed because dependent on deliverables from contract signed under TP14_151 | D. Myslikovjan
| cw04/2015 | 51) TP14_121: start postponed after discussion with Installations Manager | L. Půst
| cw04/2015 | 52) TP14_098: start postponed from 10/2014 to 01/2015; specifications were not handed over to procurement yet | M. Legát
| cw04/2015 | 53) TP14_115: tender merged with TP15_036 therefore its timing is changed according to TP15_036 | L. Nims
| cw04/2015 | 54) TP14_113, 114: tender were CANCELED; project authorities decided that they are not necessary | J. Janďourek
Version 02 2015 (February)
LT12 | cw07/2015 | 01) TP14_112: start rescheduled in Phase 2 into 10/2015 according to RP4 leader information | J. Andreasson
| cw08/2015 | 02) TP14_030: Publication set to 01/04/2015; price lowered from 15M CZK to less than 2M CZK | B. Le Garrec
| cw08/2015 | 03) TP15_006: Set initial deadlines with respect to first deliveries to be ready in ELI by 1Q/2016 for LUX, HHG, PXS | V. Olšovcová
| cw09/2015 | 04) TP15_043: new tender for TMP pumps for experimental needs | L. Brabec
| cw09/2015 | 05) TP15_010: tender moved into Phase 2, year 2016 | V. Krpálková
| cw09/2015 | 06) TP14_120: tender failed due to formally incorrect bids and will be re-issued; new Publication deadline set to 27/02/2015 (announced by M. Legát as a deputy to D. Pokorný) | D. Pokorný
| cw09/2015 | 07) TP15_005, 110: tenders are not accounted as Phase 1 drawing cost thus rescheduled into Phase2 by RP2 leader | S. Sebban
| cw09/2015 | 08) TP15_004, 009: tenders are not accounted as Phase 1 drawing cost thus rescheduled into Phase2 by research leader | T. Laštovička
| cw09/2015 | 09) TP14_012, 013: were out-merged | M. Legát
| cw09/2015 | 10) TP14_042+133: Publication delayed from 01/03/2015 due to delayed specification from BDS group | M. Körber
| cw09/2015 | 11) TP14_022: Publication delayed from 01/02/2015 to 10/04/2015; delayed specification to cw10/2015 | D. Kurz
| cw09/2015 | 12) TP15_045: new Building related tender pasted into schedule | M. Chudožilov
| cw09/2015 | 13) TP14_094: specs delayed; start postponed from 09/02/2015; according RP1 leader they will be ready soonest by 30/03/2015 | D. Kurz
| cw09/2015 | 14) TP15_039: Procurement informed about delayed Publication from 15.2.2015 | D. Pokorný
| cw09/2015 | 15) TP14_016, 017: postponed start from 16/02/2015 to 03/03/2015; Publication date remains unchanged | D. Pokorný
| cw09/2015 | 16) TP14_008, 039; TP15_029, 030, 031, 032, 035: all items are processed through Dynamical Procurement System (DNS) and all have delayed Publication from 02/2015 into 2nd half of 03/2015; reason for delay: contract with supplier for DNS was has been concluded late | A. Csabová
| cw09/2015 | 17) TP15_047, 048, 049: new items | J. Andreasson
| cw09/2015 | 18) TP14_023: BDS leader rescheduled tender into Phase 2 (2016) | B. Le Garrec
| cw09/2015 | 19) TP14_167, 169: BDS leader announced new Publication date to 15.4.2015 | B. Le Garrec
| cw09/2015 | 20) TP14_152, 154: BDS leader rescheduled tender into Phase 2 (2017) | B. Le Garrec
| cw09/2015 | 21) TP14_035: BDS leader announced new Publication date to 2.6.2015 | B. Le Garrec
| cw09/2015 | 22) TP14_038: BDS leader rescheduled tender into Phase 2 (late 2015) | B. Le Garrec
| cw09/2015 | 23) TP14_166: BDS leader informed about tender cancelation | B. Le Garrec
| cw09/2015 | 24) TP14_049, TP15_050: BDS leader rescheduled tender into Phase 2 (2016) | B. Le Garrec
| cw09/2015 | 25)TP14_071: L1 leader informed about tender cancelation | P. Bakule
| cw09/2015 | 26) TP14_147: set initial tender timing, will be confirmed by L1 leader | D. Myslikovjan
| cw09/2015 | 27) TP14_153: Procurement informed about date of Publication | D. Pokorný
| cw09/2015 | 28) TP14_040, 129: Procurement informed about Publication date at 09/03/2015 | A. Csabová
| cw09/2015 | 29) TP15_044: new item | M. Vích
| cw09/2015 | 30) TP15_025 and 028 merged on request from IT leader into one DNS tender | M. Razým
| cw09/2015 | 31) TP14_125: changed spec. responsible from J. Vaculík to A. Oláh; Publication postponed for 2M from 17/02/2015 | D. Kurz
| cw09/2015 | 32) TP15_036 + TP14_115: out-merging these two tenders is in consideration; postponed Publication from 28/02/2015 to 15/03/2015 | M. Legát
| cw09/2015 | 33) TP14_061: specification not available; Publication postponed for 2M from 17/02/2015 | P. Bakule
| cw09/2015 | 34) TP14_067: Feb15: L1 leader changed scope and schedule; Publication postponed from 20/02/2015 to 06/2015 | P. Bakule
| cw09/2015 | 35) TP14_073: Feb15: L1 leader changed scope and schedule; Publication postponed from 12/03/2015 to 20/04/2015 | P. Bakule
| cw09/2015 | 36) TP14_098: L3 teamleader: realization via Excemption buys and minitenders; rest in VZMR moved from 28.2.2015 to 06/2015 | J. Thoma
| cw09/2015 | 37) TP15_002: Publication is being postponed for next month due to missing approved specification | D. Pokorný
| cw09/2015 | 38) TP15_007: Publication is being postponed for next two months due to missing approved specification | D. Pokorný
| cw09/2015 | 39) TP14_118: Publication is being postponed for next two months due to missing approved specification | D. Pokorný
| cw09/2015 | 40) TP15_001, 008, 014, 015, 017, 018, 019, 020: updated planning according to RP4 System schedule | D. Myslikovjan
| cw09/2015 | 41) TP15_038: slightly modified schedule according to Proc info | M. Legát
| cw09/2015 | 42) TP15_022: Publication delayed 1M from 15/02/2015 due to missing specification | M. Körber
| cw09/2015 | 43) TP15_033: Procurement work hasn't been started (15/02/2015)-missing specification from tech. team; start postponed to 3.3.2015 | A. Csabová
| cw09/2015 | 44) TP14_024: Publication delayed from 17/02/2015 to 30/03/2015, reason: tender spec. changes, tender splits to different parts | A. Csabová
| cw09/2015 | 45) TP14_037: Procurement work hasn't been started (15/02/2015)-missing specification from tech. team; start postponed to 3.3.2015; Publication postponed from 26/03/2015 to 13/04/2015 | A. Csabová
| cw09/2015 | 46) TP15_108: delayed Publication from 20/03/2015 to 13/04/2015 due to missing specification | D. Pokorný
Version 03 2015 (March)
Mar15 | cw10/2015 | 01) TP15_049: start moved into Ph2 02/2016 from 04/2015 according to information from RP4 leader | J. Andreasson
| cw12/2015 | 02) TP14_143: Publication postponed from 27/03/2015 to 27/04/2015 due to missing specs. | M. Legát
| cw12/2015 | 03) TP15_002: Publication postponed from 15/03/2015 to 15/04/2015 due to still changes in tender documentation | D. Pokorný
| cw12/2015 | 04) TP14_153: Publication postponed 1M from 15/03/2015 due to reduced scope of tender (price reduced from 8M to 5M) | D. Pokorný
| cw13/2015 | 05) TP14_004: tender CANCELED; tender was related to CITT department which suppressed its activities | A. Csabová
| cw13/2015 | 06) TP14_008: tender Publication postponed from 30/03/2015 to 30/04/2015 -external administrator hasn't finished tender documentation yet | A. Csabová
| cw13/2015 | 07) TP15_053, 054: new items | M. Körber
| cw13/2015 | 08) TP15_055: new item; main tender supplemented by already contracted Small Cost DAQ Computers (TP15_034) | A. Csabová
| cw13/2015 | 09) TP14_040: Canceled merging with TP14_129; CS HW leader postponed tender from 03/2015 into Phase 2 due to unprepared specifications from all over participating experimental teams | A. Csabová
| cw13/2015 | 10) TP14_129: merging with TP14_040 canceled; tender CANCELED, all specified equipment is procured via TP15_055; this EXP equipment is completely paid by BDS CS group | D. Myslikovjan
| cw13/2015 | 11) TP14_057: tender tracking is canceled; equipment is being purchased via Small Cost buys and orders from frame contract TP14_165 | D. Myslikovjan
| cw13/2015 | 12) TP15_057: new item added on ad-hoc request from CITT | M. Razým
| cw13/2015 | 13) TP14_125: specification delayed; tender Publication postponed next 2 weeks from 17/04/2015 to end of 04/2015 | D. Kurz
| cw13/2015 | 14) TP14_018: Management decided to brake-down the tender into 3 standalone ones: TP14_018, TP15_059, TP15_060; new dates set | D. Kurz
| cw13/2015 | 15) TP15_058: new item (Small Scale Public Contract) already contracted; added for information purposes only | M. Legát
| cw13/2015 | 16) TP14_119: tender renewed upon request from head of Engineering department | P. Korouš
| cw14/2015 | 17) TP14_115 and TP15_036 were merged out from each other and continue as standalone tender procedures | L. Nims
| cw14/2015 | 18) TP14_143: Mr. LeGarrec announced finalization of technical specification to 30/04/2015; tender Publication thus rescheduled from 27/03/2015 into 15/05/2015 | M. Legát
| cw14/2015 | 19) TP14_012: Publication postponed by 1M from 30/04/2015 due to missing specifications | M. Legát
| cw14/2015 | 20) TP14_014: missing Management decision regarding tender proceeding; Publication postponed by 1M from 10/04/2015 | M. Legát
| cw14/2015 | 21) TP15_040: Publication delayed by 3 weeks from 15/03/2015; specification and tender documentation preparation has been prolonged | D. Pokorný
| cw14/2015 | 22) TP15_041, 42: Publication delayed by 1M from 15/03/2015; specification and tender documentation preparation has been prolonged | M. Körber
| cw14/2015 | 23) TP15_056: new item | M. Razým
| cw14/2015 | 24) TP15_061: new item | D. Kurz
| cw14/2015 | 25) TP14_156: Publication postponed from 01/03/2015 to 15/04/2015 due to late specification | D. Pokorný
| cw14/2015 | 26) TP14_130: prolonged contract negotiation phase by 1M; previous contract milestone was 30/03/2015 | D. Pokorný
| cw14/2015 | 27) TP14_103, 104: contract negotiation period has been prolonged by 2 weeks | D. Pokorný
| cw14/2015 | 28) TP14_024: Publication postponed from 30/03/2015 by two weeks due to illness of spec. responsible person (tender documentation wasn't revised in time) | A. Csabová
| cw14/2015 | 29) TP15_011: Publication postponed from 15/03/2015 to 10/04/2015; later external administration, later Management approval | D. Pokorný
| cw14/2015 | 30) TP14_030: Publication date postponed by 1M from 01/04/2015 -no response from BDS team regarding tech. specification | A. Csabová
| cw14/2015 | 31) TP14_034, 036, 078: bidding period deadline postponed to 12/05/2015, thus contract milestone delays to 30/06/2015 from 30/04/2015 | A. Csabová
| cw14/2015 | 32) TP14_167+169: Publication date postponed by 1M from 15/03/2015 -Procurement has no specification from BDS | A. Csabová
| cw14/2015 | 33) TP15_029+030+031, 032: Mar15: Publication delayed by 1M from 30/03/2015: late ELI conception statement to DNS provider | A. Csabová
| cw14/2015 | 34) TP15_033: Publication postponed by 1M from 13/04/2015: late ELI conception statement to DNS provider | A. Csabová
| cw14/2015 | 35) TP14_039: specification changed twice, Publication process is prolonged by 1M from 30/03/2015 | A. Csabová
| cw14/2015 | 36) TP15_035: Publication postponed by 1M from 30/03/2015: late ELI conception statement to DNS provider | A. Csabová
| cw14/2015 | 37) TP15_062, 063: new items on request of L. Půst | L. Půst
| cw14/2015 | 38) TP14_073: Procurement informed about posponed schedule confirmed by L1 leader; Publication postponed from 20/04/2015 to 1/11/2015 | D. Kurz
| cw14/2015 | 39) TP15_021: Tender moved into Phase2 from 05/2015; confirmed by L1 leader | D. Kurz
| cw14/2015 | 40) TP15_022: 1M delay of Publication (from 15/03/2015); specs were late | M. Körber
| cw14/2015 | 41) TP14_042+133: delayed specification, Publication postponed by 1M from 5/5/2015 | M. Körber
| cw14/2015 | 42) TP15_025+028: Publication postponed by 1M from 15/04/2015: late ELI conception statement to DNS provider | M. Razým
| cw14/2015 | 43) TP14_118: tender CANCELED and was substituted (broken-down) into TP15_064, 065, 066 and 067; deadlines were copied | P. Korouš
| cw14/2015 | 44) TP15_003: prolonged contracting period by 2M from 24.2.15: longer bidding period for foreign supplier, incomplete bid claim | M. Körber
| cw14/2015 | 45) TP14_160: prolonged contract negotiation phase -specs negotiation has been longer, ex ANTE sent 25.3.2015 | M. Körber
| cw14/2015 | 46) TP14_159: prolonged EX ANTE check period, first request sent 26.2.2015 | M. Körber
| cw14/2015 | 47) TP14_048: prolonged negotiation period, negotiations with suppliers regarding final specs | D. Kurz
Version 04 2015 (April)
Apr15 | cw15/2015 | 01) TP15_007: delayed Publication by 3 weeks from 10/04/2015 to 24/05/2015 due to tender administration mistake and necessity to change Preliminary notice | D. Pokorný
| cw16/2015 | 02) TP15_068, 069, 072: new item | A. Csabová
| cw18/2015 | 03) TP15_069, 072: new items | A. Oláh
| cw18/2015 | 04) TP15_073: new item on request from Engineering department | L. Brabec
| cw18/2015 | 05) TP14_163: tender postponed by requestors into 2016 from 04/2015 | D. Kurz
| cw19/2015 | 06) TP15_039: miniTender has been canceled; now subject to transformation into DNS; Publication date moved from 25/03/2015 to 30/05/2015 | A. Csabová
| cw19/2015 | 07) TP14_013: tender scope has not been approved; Publication postponed from 30/04/2015 to 30/05/2015 | M. Legát
| cw19/2015 | 08) TP14_014: missing specs, missing Management decision regarding tender launch; postponed by 1M from 10/05/2015 to 10/06/2015 | M. Legát
| cw19/2015 | 09) TP14_018, TP15_059, 060: late specifications, Publication postponed from 30/04/2015 to 30/05/2015 | A. Oláh
| cw19/2015 | 10) TP14_021 (Laundry servs): tender Publication moved into 1Q 2016 from 27/04/2015 | R. Kočová
| cw19/2015 | 11) TP14_125: specification delayed; tender Publication postponed by 1 month from 1/5/2015 | D. Kurz
| cw19/2015 | 12) TP14_023, 025: specification delayed; tender Publication postponed by 1 month from 1/5/2015 | A. Csabová
| cw19/2015 | 13) TP14_024: Publication delayed from 15/04/2015 to 10/05/2015 due to Management sign-off delays | A. Csabová
| cw19/2015 | 14) TP14_137: changed price from 8,2M to 20M CZK; 2nd round negotiation ongoing | A. Csabová
| cw19/2015 | 15) TP15_036 tender failed, no relevant bid obtained; relaunch scheduled to 13.5.2015 | M. Legát
| cw19/2015 | 16) TP15_055: bidding period was prolonged to 16.6.2015; contract estimated at 04/08/2015 | A. Csabová
| cw19/2015 | 17) TP14_008: tender EX ANTE approval pending from 21/04/2015; Publication postponed from 30/04/2015 to 20/05/2015 | A. Csabová
| cw19/2015 | 18) TP14_030: specification delayed; tender Publication postponed by 1 month from 1/5/2015 | A. Csabová
| cw19/2015 | 19) TP14_167+169: Publication date postponed from 15/04/2015 to 1.6.2015 -Procurement has no specification from BDS | A. Csabová
| cw19/2015 | 20) TP15_029, 030, 031, 035: tender's EX ANTE approval pending from 21/04/2015; Publication postponed from 30/04/2015 to 20/05/2015 | A. Csabová
| cw19/2015 | 21) TP14_039: detailed specification to Frame contract is missing; Publication postponed to 15/5/2015 from 30/04/2015 | A. Csabová
| cw19/2015 | 22) TP14_042+133: delayed specification to 30/05/2015, Publication postponed from 5/6/2015 to 5.7.2015 | M. Körber
| cw19/2015 | 23) TP15_071: new item | M. Razým
| cw19/2015 | 24) TP14_048: negotiations still continue; Procurement optimistic forecast of contract signature has been postponed from 30/5/2015 to 1/7/2015 | D. Kurz
| cw19/2015 | 25) TP14_103: contract negotiation period has been prolonged by 1M from 14/05/2015 | D. Pokorný
| cw19/2015 | 26) TP15_051: tender CANCELED; equipment has been substituted by Holzworth generator baught as a bundle of SmallCost purchases | D. Kurz
| cw20/2015 | 27) TP15_047: specification is missing; Publication postponed from 15/04/2015 to 15/06/2015 | M. Körber
| cw20/2015 | 28) TP14_130: VUV Elipsometry -prolonged contract negotiation phase by 1M; previous contract milestone was 30/04/2015 | D. Pokorný
| cw20/2015 | 29) TP15_108: delayed Publication from 13/04/2015 due to missing specification | D. Pokorný
| cw20/2015 | 30) TP14_159, 160: EX ANTE expression is missing; estimated contract milestone | M. Körber
| cw20/2015 | 31) TP14_131, TP15_003: contract negotiations continue; estimated contract milestone | M. Körber
| cw20/2015 | 32) TP15_008: Publication postponed from 04/05/2015 due to missing specification | M. Körber
| cw20/2015 | 33) TP14_116: Publication postponed from 09/05/2015 due to missing specification | D. Pokorný
| cw20/2015 | 34) TP15_043: tech. specs available after 15/05/2015; Publication postponed by 0,75M from 15/04/2015 | M. Körber
| cw20/2015 | 35) TP15_070: new item | L. Půst
| cw20/2015 | 36) TP15_040, 041, 042: tender documentation changes; Publication postponed from 15/04/2015 to 15/05/2015 | M. Körber
| cw20/2015 | 37) TP15_002: Publication postponed by 1M from 15/04/2015 due to changes in tender documentation | D. Pokorný
| cw20/2015 | 38) TP14_061, 123: Publication postponed to 30/05/2015 from 15/04/2015 due to unprepared specification | M. Legát
| cw20/2015 | 39) TP14_094: L3 compressor vessel - Publication postponed from 15/05/2015 to 17/09/2015 due to problems in design; i.e. specification to Procurement is missing; information sourced from update of L3 system schedule | A. Mlích
| cw20/2015 | 40) TP14_120: tender failed again; next re-launch assumed in July = Publication changed from 12/03/2015 to 1/06/2015 | D. Pokorný
Version 05 2015 (May)
May15 | cw22/2015 | 01) TP15_074: added to schedule ad hoc; no previous announcement; contracted 20/05/2015; contract no. S15_088E | D. Myslikovjan
| cw22/2015 | 02) TP15_075: new item on request of T. Levato | T. Levato
| cw23/2015 | 03) TP15_076: new item on request of D. Margarone | D. Margarone
| cw23/2015 | 04) TP15_025: CANCELED by requestor | M. Razým
| cw23/2015 | 05) TP15_028: out-merged from TP15_025 and STOPPED by Finance management due to lack of funds | M. Razým
| cw23/2015 | 06) TP14_033: Updated schedule based on new BDS System Schedule from 1.6.2015 | D. Myslikovjan
| cw23/2015 | 07) TP14_159: prolonged bidding period, postponed contract milestone from 10/06/2015 to 30/7/2015 | M. Körber
| cw23/2015 | 08) TP14_131: prolonged bidding period, postponed contract milestone from 30/06/2015 to 30/07/2015 | M. Körber
| cw23/2015 | 09) TP14_160: prolonged bid evalution period, postponed contract milestone from 30/05/2015 to 30/06/2015 | M. Körber
| cw23/2015 | 10) TP15_008: Publication postponed by requestor from 04/06/2015 to 01/08/2015 | M. Körber
| cw23/2015 | 11) TP15_047: delayed specification; Publication postponed from 15/06/2015 to 30/07/2015 | M. Körber
| cw23/2015 | 12) TP15_049: delayed specification; Publication postponed from 1/06/2015 to 15/08/2015 | M. Körber
| cw23/2015 | 13) TP14_042+133: Publication postponed from 15/07/2015 to 30/09/2015, requestor announced available specification no earlier than in 15.8.2015 | M. Körber
| cw23/2015 | 14) TP15_053: missing specification, postponed from 15/05/2015 to 01/08/2015 due lower management priorities | M. Körber
| cw23/2015 | 15) TP15_022: failed in May, formally wrong bid, subject to re-launch by end of June 2015 | M. Körber
| cw23/2015 | 16) TP14_143: delayed spec finalized, Publication postponed from 15/05/2015 to 08/06/2015 | M. Körber
| cw23/2015 | 17) TP14_014: missing specs, missing Management decision regarding tender launch; postponed by 1M from 10/06/2015 to 10/07/2015 | M. Legát
| cw23/2015 | 18) TP15_060: changed Management strategy; Publication postponed from 30/05/2015 to 30/06/2015 | M. Razým
| cw23/2015 | 19) TP15_063: not clear specification and financing; Publication postponed from 30/04/2015 to 01/07/2015 | M. Razým
| cw23/2015 | 20) TP14_167+169: BDS leader announced specifications to be ready by 05/06/2015; Publication postponed from 01/06/2015 to 15/07/2015 | D.Kurz
| cw23/2015 | 21) TP15_043+073: tenders have been merged; Publication for both postponed from 06/2015 to 15/07/2015 due to delayed specification | M. Körber
| cw23/2015 | 22) TP15_036: specification is still being reworked; Publication postponed from 13/05/2015 to 30/06/2015 | M. Legát
| cw23/2015 | 23) TP15_071: tender changed specification and cost to over-limit; Publication postponed from 1/6/2015 to 1/7/2015 | M. Razým
| cw23/2015 | 24) TP14_061, 123: Publication postponed from 30/05/2015 to 30/06/2015, missing specification | M. Legát
| cw23/2015 | 25) TP14_094: specification not ready; Publication postponed from 1/6/2015 to 10/07/2015 | D. Kurz
| cw23/2015 | 26) TP15_064, 066: specification not ready; Publication postponed from 20/4/2015 to 15/07/2015 | M. Razým
| cw24/2015 | 27) TP15_059: Management decision regarding tender realization is pending; Publication postponed from 30/05/2015 to 30/06/2015 | Z. Poupová
| cw24/2015 | 28) TP14_119: specifications not ready; Publication postponed from 26/04/2015 to 15/07/2015 | Z. Poupová
| cw24/2015 | 29) TP15_062: Financing issues; Publication postponed from 30/04/2015 to 30/06/2015 | A. Oláh
| cw24/2015 | 30) TP15_065, 067: specs not ready; Publication postponed from 20/04/2015 to 15/07/2015 | K. Hamouzová
| cw24/2015 | 31) TP15_056: May15: specs not ready; Publication postponed from 01/06/2015 to 01/07/2015 | M. Razým
| cw24/2015 | 32) TP14_012: Final specs pending, work on tender documentation, Publication postponed from 30/05/2015 to 19/06/2015 | J. Nawratová
| cw24/2015 | 33) TP15_072: delayed 1M due to Proc. personel load; Publication postponed from 15/05/2015 to 12/06/2015 | J. Nawratová
| cw24/2015 | 34) TP14_115: May15: missing specifications, Publication postponed from 04/05/2015 to 04/07/2015 | M. Legát
| cw24/2015 | 35) TP15_041 and 042 have been published by 13/05/2015 | M. Razým
| cw24/2015 | 36) TP15_040: ready for Publication (scheduled to 04/06/2015) | D. Pokorný
| cw24/2015 | 37) TP15_029, 031: DNS ready to start at 05/06/2015 (Publication postponed from 30/04/2015); out-merged all of TP15_029, 030 and 031 | A. Csabová
| cw24/2015 | 38) TP15_030: Published by 27/05/2015 | A. Csabová
| cw24/2015 | 39) TP15_068 tender iwill be ready to Publication by 2.6.2015 | A. Csabová
| cw24/2015 | 40) TP14_121: ongoing discussions regarding funding and scope; Publication postponed from 01/05/2015 to 01/07/2015 | D. Myslikovjan
| cw24/2015 | 41) TP14_025: May15: specification delayed; tender Publication postponed by 1 month from 1/6/2015 to 01/07/2015 | A. Csabová
| cw24/2015 | 42) TP15_078, 079: new items added after late announcement from Procurement | A. Csabová
| cw24/2015 | 43) TP14_035: May15: BDS leader announced new Publication date to 1.07.2015 (in System Schedule) | A. Csabová
| cw24/2015 | 44) TP14_030: CANCELED on request from BDS leader (mailed 26.5.2015) | J. Sýs
| cw24/2015 | 45) TP14_023: delayed specs, BDS leader has postponed Publication date to 1/07/2015 from 01/06/2015 | A. Csabová
| cw24/2015 | 46) TP14_008: Ex ANTE finished 28/05/2015; Publication postponed from 20/05/2015 to 12/06/2015 | A. Csabová
| cw24/2015 | 47) TP15_033, 035: : Ex ANTE finished 28/05/2015; Publication postponed from 20/05/2015 to 12/06/2015 | A. Csabová
| cw24/2015 | 48) TP14_117: dependent on TP14_151 results which are known by end of May 2015; Publication postponed from 05/2015 to 09/07/2015 | A. Csabová
| cw24/2015 | 49) TP14_034+036+078: tender failed and is subject to re-issue in mid of June 2015 | M. Razým
| cw24/2015 | 50) TP14_116 and 117: tenders renamed and broken-down (to TP14_116, 117, TP15_080, TP16_003, TP17_003, 004)according to new specification and timing from Safety leader; | P. Procházka
Version 06 2015 (June - July 2015)
Jul15 | cw25/2015 | 01) TP15_049: tender has been canceled upon RP4 WP report from May 2015 | J. Andreasson
| cw26/2015 | 02) TP15_082: new item added on request of ITC leader | J. Charfreitag
| cw26/2015 | 03) TP14_163: tender CANCELED by requestor | D. Kurz
| cw26/2015 | 04) TP16_004: new item on request of Procurement/Safety | D. Kurz
| cw31/2015 | 05) TP15_073: part of this tender (450k from 1303k CZK) has been separated into ne tender TP15_083; new tender cost resulted in 950k CZK and is still merged with TP15_043 | L. Brabec
| cw31/2015 | 06) TP15_083: New item which has been created from TP15_073; tender has been published by 16/07/2015 | M. Legát
| cw31/2015 | 07) TP15_064: into this one ref. number have been merged three tenders for machinery of mechanical workshop: TP15_064 (turning machine), TP15_066 (3-axis Milling machine) and TP15_067 (LCV550 Accessories); Publication deadline for this new merged tender has been set to 30.8.2015 | P. Korouš
| cw31/2015 | 08) TP15_066, 067: tenders have been canceled, theirs content has been merged into scope of TP15_064 | P. Korouš
| cw31/2015 | 09) TP15_096, 097, 098, 099, 100, 101: new item; broken-down from generic Installation tender TP14_121 | M. Berta
| cw31/2015 | 10) TP15_063: Market Research on way, Publication date has been set accordingly | A. Oláh
| cw31/2015 | 11) TP15_095: new item defined by Installation team | M. Berta
| cw31/2015 | 12) TP15_014-020: updated planning according to RP4 System schedule | J. Andreasson
| cw31/2015 | 13) TP15_084: new item on request from RP3 leader | D. Margarone
Version 07 2015 (August 2015)
Aug15 | cw35/2015 | 01) TP15_002: Decided to stop RP4 part due to budget issues; RP4 part (5,5M CZK ex VAT) to be realised in 2016 as TP16_005 | D. Pokorný
| cw35/2015 | 02) TP15_111: new item - formerly part RP4 of TP15_002 (xRay CCDs) | D. Kurz
| cw35/2015 | 03) TP15_062, 096, 097, 098, 099, 100, 101: Publication postponed from 30/08/2015 to 30/09/2015 due to delayed specification from Requestor | M. Berta
| cw35/2015 | 04) TP14_116: Publication changed from 12/2015 to 15/10/2015 upon request of Safety leader | D. Kurz
| cw35/2015 | 05) TP15_094: requestor has not specs and RSD prepared, Publication postponed from 10/09/2015 to 10/10/2015 | J. Hejduková
| cw35/2015 | 06) TP15_087, 088: CANCELED by Requestor; realisation via Low Cost purchases | D. Myslikovjan
| cw35/2015 | 07) TP15_075: CANCELED by Requestor; realisation via MEYS Excemption purchase | M. Razým
| cw35/2015 | 08) TP15_084: changed scope and price; Published by 17/08/2015 | M. Legát
| cw35/2015 | 09) TP15_112: new item on behalf of BDCS leader | M. Legát
cw35/2015
cw35/2015
cw35/2015
cw35/2015
Sep15 | cw39/2015 | 01) TP15_113, 114, 116: new items on request from L1 team leaders | P. Bakule

## List1 (hidden)
Groups
G001
G002
G003
G004
G005
G006
G007
G008
G009
G010
G011
G012
G013
G014
G015
G016
G017
G018
G019
G020
G021
G022
G023
G024
G025
G026
G027
G028
G029
G030
G031
G032
G033
G034
G035
G036
G037
G038
G039
G040
G041
G042
G043
G044
G045
G046
G047
G048
G049
G050
G051
G052
G053
G054
G055
G056
G057
G058
G059
G060
G061
G062
G063
G064
G065
G066
G067
G068
G069
G070
G071
G072
G073
G074
G075
G076
G077
G078
G079
G080
G081
G082
G083
G084
G085
G086
G087
G088
G089
G090
G091
G092
G093
G094
G095
G096
G097
G098
G099
G100
G101
G102
G103
G104
G105
G106
G107
G108
G109
G110
G111
G112
G113
G114
G115
G116
G117
G118
G119
G120
G121
G122
G123
G124
G125
G126
G127
G128
G129
G130
G131
G132
G133
G134
G135
G136
G137
G138
G139
G140
G141
G142
G143
G144
G145
G146
G147
G148
G149
G150
G151
G152
G153
G154
G155
G156
G157
G158
G159
G160
G161
G162
G163
G164
G165
G166

## List_box (hidden)
item no. | Value
1 | legal prep
2 | approvals
3 | qualification
4 | published
5 | bidding
6 | bid evaluation
7 | contracted
8 | specs delayed
9 | canceled

## Total PFP (hidden)
PFP Ph1 September 2015 | LSR | BDCS | EXP | INST | Total
Contracts 2015 | 542.4 | 90.196 | 110.754 | 0.2 | 743.55
Plan Ph1 cost | 83.255 | 51.16 | 44.436 | 3.067 | 181.918 | edituj tento řádek pro výpočet vlivu krit. VŘ
Budget Ph1 | 2081.869 | 287.307 | 251.512 | 5.32 | 2626.008
Disbursement until 12/2014 | 1634.2 | 66.8 | 46.5 | 0 | 1747.5
XPh1 | 625.655 | 141.356 | 155.19 | 3.267 | 925.468
RPh1 | 447.669 | 220.507 | 205.012 | 5.32 | 878.508
PFP | 1.3976 | 0.64105 | 0.75698 | 0.6141 | 1.0535
% from Rph1 | -39.76% | 35.9% | 24.3% | 38.59% | -5.345%
Cost balance (M CZK) | -177.986 | 79.151 | 49.822 | 2.053 | -46.96
% from Budget Ph1 | -8.549% | 27.55% | 19.81% | 38.59% | -1.788%
PFP Ph2 September 2016 | Budget Ph1 | Plan cost | Commitments | Disbursement | P + D + C | XPh2 | RPh2 | PFP index | Cost balance (M CZK) | % from Budget Ph1
Installations
Lasers
Central Vacuum
Workshops
BDS+BT Vacuum
CS
Safety
CleanRooms
Experiments + Exp SupSys

## L3L4 (hidden)
| Rozpočet | Výdaje | Plán Tendrů | Plán MN | Smlouvy (dosud nezaplaceno) | Bilance | Poznámka
Laser 3 | 113822500 | 81624369.76 | #REF! | ? | 67887480 | #REF! | Ve výdajích započten ETOP Ph2 za 38,9 M a Beta Ti:S hlavice za 10,7M
Laser 4 | 643243190 | 140489322.22 | #REF! | ? | 395215246.1 | #REF!

## Procurement plan
Tender ref. code | System | Tender name | Contract type | Tender Cost ( CZK ex VAT) | Proc contact | Proc contact | E-mail Address
Non-Technology |  |  |  | 16500000 | separator
| Management |  | Plan cost: | 16500000 | separator
TP17_015 | Mngmt IT | TC - SW services and development | Services | 5600000 | 2017-03-24 | Matúš Legát | matus.legat@eli-beams.eu
TP17_016 | Mngmt IT | SW licences for personal computers and servers 2017 | Services | 900000 | 2017-02-10 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_164 | Mngmt | Legal consultancy services (framework contract) | Supply | 10000000 | 2016-09-20 | Michal Razým | Michal.Razym@eli-beams.eu
| Building ICT |  | Plan cost: | 0 | separator
| Building |  | Plan cost: | 86990000 | separator
TP16_010 | Building | Maintenance Consuambles / Spotřební materiál - Údržba | Supply | 2000000 | 2017-02-28 | Martin Körber | Martin.Korber@eli-beams.eu
TP16_102 | Building | Monitoring system of cleanliness of Clean rooms | Supply | 1000000 | 2017-10-15 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_196 | Building | Technical supervision of floors defects removal/reconstruction | Services | 1990000 | 2016-12-13 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_198 | Building | Cleaning services (clean rooms) ELI beamlines 4-5,0 M CZK/Year | Services | 20000000 | 2017-02-28 | Martin Körber | Martin.Korber@eli-beams.eu
TP16_199 | Building | Building maintanance and inspections | Services | 2500000 | 2017-03-30 | Martin Körber | Martin.Korber@eli-beams.eu
TP17_019 | Building | Gardening, external cleaning | Services | 2000000 | 2017-06-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_020 | Building | Clean rooms machinery (big cleaning machines) | Supply | 2000000 | 2017-10-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_021 | Building | Clean rooms machinery (small particle counters) | Supply | 2000000 | 2017-09-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_022 | Building | FM | Services | 7500000 | 2017-05-20 | Matúš Legát | matus.legat@eli-beams.eu
TP17_023 | Building | Clean rooms - Consuambles 2 (framework) | Supply | 7500000 | 2017-07-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_024 | Building | Clean rooms validation | Services | 2000000 | 2017-04-07 | Michal Razým | Michal.Razym@eli-beams.eu
TP17_025 | Building | HVAC cascade regulation | Services | 2000000 | 2017-04-07 | Michal Razým | Michal.Razym@eli-beams.eu
TP17_026 | Building | Filters to air-conditioning | Supply | 7500000 | 2017-07-10 | Matúš Legát | matus.legat@eli-beams.eu
TP17_035 | Building | Automatic horizontal Air vent stainless steel | Supply | 2000000 | 2017-04-20 | David Kurz | David.Kurz@eli-beams.eu
TP17_037 | Building | Demolition works in E3 experimental hall | Services | 5000000 | 2017-04-30 | Martin Körber | Martin.Korber@eli-beams.eu
TP17_038 | Building | Reconstruction for the rest of Experimental floors | Services | 20000000 | 2017-04-30 | Martin Körber | Martin.Korber@eli-beams.eu
Technology |  |  |  | 496973495.105 | separator
| Beam Distribution Systems |  | Plan cost: | 241608507 | separator
TP15_024 | Beam Transport | Vacuum chamber for L1 injector | Supply | 1500000 | 2017-02-05 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_123 | Beam Transport | Adaptive mirrors L3 (former name AO loop) | Supply | 4728500 | 2017-05-30 | Martin Körber | Martin.Korber@eli-beams.eu
TP17_031 | Beam Transport | Adaptive mirrors L4 | Supply | 1 | 2017-06-01 | Matúš Legát | matus.legat@eli-beams.eu
TP16_125 | Beam Transport | L3 beamlines mirror mounts | Supply | 25110003 | 2017-07-15 | David Kurz | David.Kurz@eli-beams.eu
TP16_126 | Beam Transport | L4 beamlines mirrors | Supply | 23760000 | 2017-06-01 | David Kurz | David.Kurz@eli-beams.eu
TP16_127 | Beam Transport | L4 beamlines mirror mounts | Supply | 7560000 | 2017-06-01 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_130 | Beam Transport | L3 focusing parabolas | Supply | 27500000 | 2017-06-15 | David Pokorný | david.pokorny@eli-beams.eu
TP16_132 | Beam Transport | Optomechanics and motion systems for E1 | Supply | 3575000 | 2017-03-28 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_134 | Beam Transport | Alignment laser for L3 beamlines | Supply | 2750000 | 2017-04-30 | David Kurz | David.Kurz@eli-beams.eu
TP16_154 | Beam Transport | L3 vacuum components | Supply | 74305000 | 2016-11-18 | David Kurz | David.Kurz@eli-beams.eu
TP16_169 | Beam Transport | L4 vacuum components | Supply | 13500000 | 2017-06-01 | David Kurz | David.Kurz@eli-beams.eu
TP17_032 | Beam Transport | L3 parabola mounts | Supply | 23402500 | 2017-04-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_017 | Beam Transport | Mirrors coating | Supply | 1 | 2017-05-31 | Matúš Legát | matus.legat@eli-beams.eu
TP17_046 | Beam Transport | Merging: Group Nr. G17_046 L1-E1. Additional optics and diagnostics | Supply | 3575000 | 2017-05-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_047 | Beam Transport | L1-E1: Chamber decoupling, chambers 10-12 | Services | 825000 | 2017-05-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_048 | Beam Transport | L1-E1: Feedthroughs | Supply | 550000 | 2017-07-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_049 | Beam Transport | L1-E1: Beam delivery mechanics for SRS pump beams to other end stations | Supply | 550000 | 2017-07-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_050 | Beam Transport | Merging: Group Nr. G17_046 Reffractive telescopes for E1 (part of TP17_046) | Supply | 1 | 2017-05-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_051 | Beam Transport | Merging: Group Nr. G17_046 Beam expansion and forming of alignment laser (part of TP17_046) | Supply | 1 | 2017-05-30 | Matúš Legát | matus.legat@eli-beams.eu
TBA | Beam Transport | L3 diagnostics stations -> not on Georg's list, to be removed? (it says we are to build it inhouse) | Supply | 3987500 | unknown | Matúš Legát | matus.legat@eli-beams.eu
TBA | Beam Transport | Reflective beam demagnification for end of chain full diagnostics suite | Supply | 5500000 | unknown | Matúš Legát | matus.legat@eli-beams.eu
TBA | Beam Transport | Switchyards rotation translation -> this comes from Technology Delivery Board meeting on 4th November. Is it still valid? Is it not part of tenders above? If it is L1-E1 only than is covered by TP16_132 | Supply | 8250000 | unknown | Matúš Legát | matus.legat@eli-beams.eu
TBA | Beam Transport | Misc components | Supply | 2750000 | unknown | Matúš Legát | matus.legat@eli-beams.eu
TBA | Beam Transport | Installation | Supply | 2430000 | unknown | Matúš Legát | matus.legat@eli-beams.eu
TBA | Beam Transport | Beam down-collimation for AO and with far/near field diagnostics | Supply | 5500000 | unknown | Matúš Legát | matus.legat@eli-beams.eu
| Control Systems |  | Plan cost: | 12355200 | separator
TP14_008f | Control Systems | Small shielded cabinets (DNS passive netw. components: particular call) | Supply | 4364000 | 2017-03-30 | Michal Razým | Michal.Razym@eli-beams.eu
TP14_008i | Control Systems | Power Distribution Units to 19" racks (DNS passive netw. components: particular call) | Supply | 800000 | 2017-03-20 | Michal Razým | Michal.Razym@eli-beams.eu
TP15_029e | Control Systems | Operator computers (Control Servers DNS: particular call) | Supply | 800000 | 2017-05-17 | Michal Razým | Michal.Razym@eli-beams.eu
TP15_033b | Control Systems | Screens (Equipment for main Control Room DNS: particular call) | Supply | 500000 | 2017-01-10 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP15_035b | Control Systems | Batch #2 Vacuum, Alignment laser, Basic motion – E2-E3 | Supply | 1200000 | 2017-05-02 | Michal Razým | Michal.Razym@eli-beams.eu
TP15_035c | Control Systems | Batch #4 Vacuum, Alignment laser, Basic motion – E4 | Supply | 1000000 | 2017-05-02 | Michal Razým | Michal.Razym@eli-beams.eu
TP15_035d | Control Systems | Batch #5 Vacuum, Alignment laser, Basic motion – E5 | Supply | 1000000 | 2017-07-03 | Michal Razým | Michal.Razym@eli-beams.eu
TP16_157 | Control Systems | Merging: Group nr. G16_157 Control computers - Advanced Control Cards (failed due to formal incorrect bid; to be launched standalone again by 20.2.2017) | Supply | 826200 | 2016-11-20 | Michal Razým | Michal.Razym@eli-beams.eu
TP14_040 | Control Systems | DAQ cards (Framework contract) (renamed from "Addon cards") | Supply | 900000 | 2016-11-20 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_036 | Control Systems | PCIe Network interface cards | Supply | 965000 | 2017-03-20 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
| Laser systems |  | Plan cost: | 86001912.4934 | separator
TP14_068 | Laser 1 | Crystals 03: Main OPCPA crystals | Supply | 2172000 | 2017-05-20 | Matúš Legát | matus.legat@eli-beams.eu
TP14_147 | Laser 1 | L1_LBO_OPCPA_crystals_main_amp | Supply | 434400 | 2017-05-20 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP15_021 | Laser 1 | Set of dielectric chirped mirrors for 1 ps to 20 fs pulse compressor (cca 30 mirrors, 50mm diam | Supply | 5400000 | 2017-03-20 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_002 | Laser 1 | Main Chirped Mirror Compressor - frame & optomechanics | Supply | 772050 | 2017-03-04 | Matúš Legát | matus.legat@eli-beams.eu
TP16_044 | Laser 1 | L1_800 nm pulse picker | Supply | 330000 | on demand | Matúš Legát | matus.legat@eli-beams.eu
TP16_052 | Laser 1 | L1_LBO SHG crystal for 1J (B1 to stage7) | Supply | 1650000 | 2017-05-20 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_190 | Laser 1 | L1_vacuum side wiring, connectors and feedthoughs for OPCPA chamber | Supply | 1600000 | 2017-03-30 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_018 | Laser 1 | Wiring Accessories (framework) 1,9M | Supply | /1950000 400k L1 | 2017-02-20 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_066 | Laser 2 | L2_CS_Planned more NI RMC units | Supply | 1216156.4934 | unknown | Matúš Legát | matus.legat@eli-beams.eu
TP17_777 | Laser 2 | L2_all_small_scale_procurements_2017 (including P. Bakule's FE equipment) | Supply | 5900000 | 2017-09-05 | Matúš Legát | matus.legat@eli-beams.eu
TP16_086 | Laser 3 | PAD/SPDPS optics | Supply | 2833706 | unknown | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_162 | Laser 3 | L3 compressor optics: ultrafast mirrors CMM 1, 2 and 3 | Supply | 1630000 | 2017-02-28 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_010 | Laser 3 | Mass spectrometers | Supply | 800000 | 2017-03-24 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_090 | Laser 4 | L4_grating bezels and mounts | Supply | 6833800 | 2017-08-15 | Matúš Legát | matus.legat@eli-beams.eu
TP16_098 | Laser 4 | L4_transport mounts L4bc | Supply | 6673800 | 2017-06-20 | Martin Körber | Martin.Korber@eli-beams.eu
TP17_039 | Laser 4 | L4 tripod optomechanics functional prototype | Supply | 1200000 | 2017-07-20 | Matúš Legát | matus.legat@eli-beams.eu
TP16_179 | Laser 4 | L4_Deformable mirror, full size uncompressed | Supply | 6750000 | 2017-05-05 | Martin Körber | Martin.Korber@eli-beams.eu
TP17_040 | Laser 4 | CIS mirrors substrates | Supply | 18720000 | 2017-04-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_041 | Laser 4 | CIS mirrors coating | Supply | 3600000 | 2017-08-20 | Matúš Legát | matus.legat@eli-beams.eu
TP17_043 | Laser 4 | CIS mounts M7, M8 and M9 | Supply | 2400000 | 2017-06-05 | Matúš Legát | matus.legat@eli-beams.eu
TP17_044 | Laser 4 | CIS 1 and CIS2 chambers with all optomechanics | Supply | 11000000 | 2017-05-20 | Matúš Legát | matus.legat@eli-beams.eu
| Experimental Systems |  | Plan cost: | 47590915 | separator
| RP2 |  |  |  | separator
TP16_150 | RP2 | Motorized quadrupole systems | Supply | 1095849 | 2017-05-30 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_152 | RP2 | X-ray optics | Supply | 892566 | 2017-05-30 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
| RP3 |  |  |  | separator | #N/A | #N/A
TP15_089 | RP3 | HELL local server | Supply | 650000 | 2017-02-05 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP15_090 | RP3 | HELL electron diagnostics | Supply | 1500000 | 2017-02-17 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP15_091 | RP3 | HELL recirculation gas system | Supply | 700000 | unknown | Václav Mráz | Vaclav.Mraz@eli-beams.eu
| RP4 | VUV/soft X-ray materials science (WP 5.3.1) |  |  | separator
| RP4 | Coherent imaging and AMO (WP 5.3.2) |  |  | separator
TP16_038 | RP4 | OAP substrates for VUV multilayer reflectors (VUV Optics 1) | Supply | 4125000 | 2017-01-20 | David Pokorný | david.pokorny@eli-beams.eu
TP16_119 | RP4 | Detector for VMI spectrometer (Velocity Map Imaging) | Supply | 1215000 | 2017-02-15 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_009 | RP4 | Sample delivery and particle imaging | Services | 1925000 | 2017-01-15 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_011 | RP4 | VUV monochromator UHV chamber | Supply | 1512500 | 2017-05-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_012 | RP4 | VUV monochromator optical components | Supply | 550000 | 2017-05-30 | Matúš Legát | matus.legat@eli-beams.eu
TP17_013 | RP4 | VUV broadband refocusing optics | Supply | 550000 | 2017-05-01 | Matúš Legát | matus.legat@eli-beams.eu
TP17_014 | RP4 | High repetition rate VUV imaging camera | Supply | 1100000 | 2017-06-30 | Matúš Legát | matus.legat@eli-beams.eu
| RP4 | Optical probes and pump beams (WP 5.3.3) |  |  | separator
| RP4 | X-ray science (WP 5.3.4) |  |  | separator
TP16_027 | RP4 | X-ray diffraction station | Supply | 8000000 | 2016-10-05 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_034 | RP4 | X-ray spectroscopy detector | Supply | 825000 | 2017-07-15 | Matúš Legát | matus.legat@eli-beams.eu
TP16_039 | RP4 | Multilayer X-ray optics | Supply | 2000000 | 2017-04-15 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_138 | RP4 | Positioning Systems for E1 Endstations 2 | Supply | 1950000 | 2017-07-15 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
| RP4 | Support labs and equipment (WP 5.3.7) |  |  | separator
| RP5 |  |  |  | separator
| Exp. shared tenders |  |  |  | separator
TP15_123 | Exp. Programmes | Optomechanics for experimental programs (part "Optomechanics", formerly part 1 of TP15_108) (RP1, RP2, RP3, RP5) | Supply | 19000000 | 2016-12-16 | David Pokorný | david.pokorny@eli-beams.eu
| Engineering/Support Systems/Central Vacuum |  | Plan cost: | 10695504 | separator
TP16_100 | Engineering | Central Vacuum fittings and gauges 2 (framework) ( 6912704 ex VAT to CenVac, 1080000 to BT) | Supply | 6912704 | 2017-02-15 | Martin Körber | Martin.Korber@eli-beams.eu
TP16_187 | Engineering | Vacuum valves 2 (framework) (3782800 ex VAT account to Central Vac, 0,5M ex VAT account to BT) | Supply | 3782800 | 2017-01-20 | Martin Körber | Martin.Korber@eli-beams.eu
| Workshops |  | Plan cost: | 10822727.2727 | separator
TP16_104 | Workshops general | Metal furniture for experimental halls | Supply | 1950000 | 2017-02-15 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_005 | Workshops TL | TargetLAB equipment 1 Digital optical microscope | Supply | 2500000 | 2017-02-12 | Martin Körber | Martin.Korber@eli-beams.eu
TP17_006 | Workshops TL | TargetLAB equipment 2 | Supply | 2272727.2727 | 2017-05-08 | Matúš Legát | matus.legat@eli-beams.eu
TP17_007 | Workshops TL | Laboratory equipment 1: Cryostat | Supply | 1600000 | 2017-02-15 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP17_008 | Workshops TL | Laboratory equipment 2 | Supply | 2500000 | 2017-05-08 | Matúš Legát | matus.legat@eli-beams.eu
| Installations |  | Plan cost: | 14840000 | separator
TP15_095 | Installations | Scaffolding (framework contract for clean rooms installations) | Supply | 400000 | 2017-03-06 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_115 | Installations | Manipulation equipment for clean rooms: Telescopic work platform | Supply | 1850000 | 2016-08-30 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_193 | Installations | Gantry crane 3t | Supply | 590000 | 2017-01-24 | David Pokorný | david.pokorny@eli-beams.eu
TP17_027 | Installations | Geodetic services II | Services | 2000000 | 2017-06-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_028 | Installations | Electrotechnical job | Services | 2000000 | 2017-08-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_029 | Installations | Fine mechanics | Services | 2000000 | 2017-08-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_030 | Installations | Transportation services 2 | Services | 2000000 | 2017-10-15 | Matúš Legát | matus.legat@eli-beams.eu
TP17_031 | Installations | Vacuum systems | Services | 2000000 | 2017-08-15 | Matúš Legát | matus.legat@eli-beams.eu
TP15_101 | Installations | Installations: data infrastructure (cables) (framework contract) | Services | 2000000 | 2017-02-28 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
| Safety |  | Plan cost: | 58506250 | separator
TP15_006 | Safety | Radiation Shielding (universal modular equipment) | Supply | 6550000 | 2017-06-15 | David Kurz | David.Kurz@eli-beams.eu
TP16_106 | Safety | Shielding tender for PXS, RP4 | Supply | 600000 | 2017-05-15 | Matúš Legát | matus.legat@eli-beams.eu
TP14_117 | Safety | Safety systems: personal safety interlock (All in one) (NEGOTIATED procedure) Total cost is 45 702 500; from Ph2 budget is paid only XXX, rest is considered as an contract option) | Supply | 31955000 | 2016-04-30 | Michal Razým | Michal.Razym@eli-beams.eu
TP16_118 | Safety | FRAME TENDER MONITORING SYSTEM - planned to be a framework contract with total cost 34 545 545 CZK ex VAT. From Ph2 budget can be paid only 19,4M ex VAT. Financing of remaining costs is unclear and therefore realization of this tender concept has to be verified with Lawyers and Finance! | Supply | 19401250 | 2017-08-10 | Michal Razým | Michal.Razym@eli-beams.eu
| Cleanrooms & Cleaning |  | Plan cost: | 14552479.3388 | separator
TP16_181 | Cleanrooms | Laminar Fan Filter Units (flowboxes) For cleanroom tents | Supply | 900000 | 2017-05-30 | David Pokorný | david.pokorny@eli-beams.eu
TP16_182 | Cleanrooms | Demi water station | Supply | 1115702.4793 | 2017-04-30 | Václav Mráz | Vaclav.Mraz@eli-beams.eu
TP16_015 | Cleanrooms | Design and supply of cleaning technology for cleaning room(s) | Supply | 4950000 | unknown | Michal Razým | Michal.Razym@eli-beams.eu
TP17_033 | Cleanrooms | Outsourced L3 BT cleaning | Supply | 6136363.6364 | unknown | Matúš Legát | matus.legat@eli-beams.eu
TP17_034 | Cleanrooms | Outsourced L4 BT cleaning | Supply | 1450413.2231 | unknown | Matúš Legát | matus.legat@eli-beams.eu
| ELIBIO |  |  | 66169438.38 | separator
TP16_501 | ELIBIO | Synchronized pump beam laser | Supply | 14162499 | 2017-04-28 | David Pokorný | david.pokorny@eli-beams.eu
TP16_502 | ELIBIO | FTIR spectrometer with light source | Supply | 2750004 | 2017-07-17 | David Pokorný | david.pokorny@eli-beams.eu
TP16_503 | ELIBIO | Fluorescence microscope | Supply | 2612500.02 | 2017-11-14 | David Pokorný | david.pokorny@eli-beams.eu
TP16_504 | ELIBIO | Inverted Microscope | Supply | 1375000.11 | 2017-12-14 | David Pokorný | david.pokorny@eli-beams.eu
TP16_505 | ELIBIO | Deep freezers (-80°C) | Supply | 681799.95 | 2017-11-06 | David Pokorný | david.pokorny@eli-beams.eu
TP16_508 | ELIBIO | Protein purification system (PPS) | Supply | 1375000.11 | 2017-10-22 | David Pokorný | david.pokorny@eli-beams.eu
TP16_509 | ELIBIO | Dynamic laser light scattering system (services tender) | Services | 1264999.95 | 2017-11-08 | David Pokorný | david.pokorny@eli-beams.eu
TP16_511 | ELIBIO | Bio-Lab complex construction in ELI | Supply | 16219710 | 2017-06-13 | David Pokorný | david.pokorny@eli-beams.eu
TP16_512 | ELIBIO | Pressure systems (services tender) | Services | 1136300.13 | 2017-09-14 | David Pokorný | david.pokorny@eli-beams.eu